## AWS start
Start by running the foundation in AWS
Begin at step 1. These steps map to Tasks; effort is already included there. Commands are in runbook AWS 2 through AWS 5.
Step | Task IDs | Action | Lead | How to do it | Completion evidence | Runbook section
1 | B01 | Launch AWS compute | Cloud implementer | EC2 console: launch g6e.2xlarge from an AWS PyTorch GPU Deep Learning AMI; select the approved VPC/subnet, instance role and no-inbound security group; add 300 GiB encrypted gp3 EBS. | SSM session opens; nvidia-smi shows GPU; save instance and AMI IDs. | AWS 2
2 | B01 | Create storage and permissions | Cloud implementer | Create private S3 model, data, run and evaluator buckets with versioning and default KMS encryption. Trainer can read only released train/dev prefixes; evaluator answers use a separate role/bucket. | Record bucket names, key ARNs and roles; positive and denial access tests pass. | AWS 2
3 | B02 | Install the model runtime | Applied AI Engineer | Activate the AMI PyTorch environment; run bootstrap.sh from the supplied AWS ZIP on EC2. Preserve the AMI Torch version with a constraint. | CUDA/BF16 and model-class imports pass; candidate-requirements.txt saved. | AWS 3
4 | B03 | Choose an exact foundation revision | Head of Product and AI | Pin the full commit using Hugging Face repository history before AWS setup, or the helper in a developer environment. On EC2, use foundation_download.py --resolve-only to check the candidate. Download the reviewed SHA even if main has advanced. | Approved full commit SHA and license evidence recorded. | AWS 3
5 | B04 | Download the foundation into AWS | Applied AI Engineer | Run foundation_download.py --revision FULL_SHA on EC2. Weights, config, tokenizer and image processor land in /srv/broadbridge/models/Qwen3.5-4B/FULL_SHA. | Shard references resolve; artifact hashes and manifest written. | AWS 3
6 | B04 | Back up the model in S3 | Applied AI Engineer | Copy the local revision directory to s3://MODEL_BUCKET/foundation/Qwen3.5-4B/FULL_SHA/ using aws s3 sync and KMS encryption. | List object count, verify representative downloads against local SHA256; save S3 URI. | AWS 4
7 | B05 | Run text and image questions | Applied AI Engineer | Run foundation_smoke.py with --model local revision directory and --image fixtures/demo_pressure.png. Review generated text and chart answer. | baseline_smoke.json contains actual responses, timing and peak memory. | AWS 4
8 | B06 B07 | Prove a training step and reload | Applied AI Engineer | Use the earlier synthetic training kit to audit language-only adapter targets and completion loss masks; execute ten optimizer steps; save/reload adapter against this exact AWS base. | Finite loss, actual parameter changes, correct masks and successful reload. | 14 and 15
9 | C01 C02 | Upload the first cleared source batch | Knowledge Engineer | Upload about 20 representative cleared originals with manifests to the S3 quarantine prefix. Include digital PDFs, scans and diagrams; include emails only with appropriate grants. | Every file has source ID, checksum and permitted routes. | AWS 5 and 3
10 | C03 C04 C10 | Extract and normalize evidence | Applied AI Engineer | Run isolated CPU extraction/OCR workers; save ordered text/table JSONL and PNG images to the extracted prefix; verify units and critical values. | Page/region citations and reviewable derivatives reconcile to originals. | 5 through 8
11 | D01 D02 D03 | Create the first 400 teaching examples | Knowledge Engineer | Build case families and split first; write 300 text and 100 visual prompt/completion examples with image paths and independent expert review. | train_v0.jsonl plus image assets pass schema, rights, leakage and technical checks. | 9 and 10
12 | E01 E02 F01 | Establish retrieval and a measured baseline | Applied AI Engineer | Build permissioned chunks and indexes; run the unchanged foundation on dev questions both with and without retrieval; retain scores and answers. | A measured comparison exists before domain fine-tuning. | 11 and 16
13 | F03 F04 F05 D06 D07 | Train the first adapter then expand data | Applied AI Engineer | Fine-tune a LoRA adapter on the initial released set; compare on dev; expand to 1500 text and 500 visual examples from the planned training families. | Versioned dataset and adapter; expansion is justified by observed errors. | 13 and 14
14 | F08 H03 I01 I02 I06 | Evaluate and package the chosen model | Technical Director | Use untouched test families; review failures; package exact base revision, adapter, processor, runtime and retrieval-index revision. | Independent acceptance evidence and reproducible release manifest. | 15 and 16
15 | H01 H02 H04 G4 J01 J02 | Deploy internally and pilot | Head of Product and AI | Deploy private authenticated service on separate AWS serving capacity; add source citations, logs, feedback, monitoring and rollback; run supervised internal briefs. | Approved users can submit text/images; quality, latency, cost and corrections are measured. | 17 and 18

## Start here
Broadbridge multimodal implementation
Read AWS start first then use this sheet to set the schedule
Input or result | Value | Meaning
Approved kickoff |  | Enter an Excel date. Blank means relative working-day schedule only.
Task count | 70 | Includes six delivery gates. Every status starts at Not started.
Finish working day | 152 | Calculated from all task dependencies and resource-level baseline holds.
Planned weeks | 31 | Five working days per week; holidays excluded from this model.
Earlier target weeks | 24 | Earlier CTO target. Detailed dependencies and resource reservations revise timing.
Difference in weeks | 7 | The earlier 24-week budget and eight-week first tranche must be rebaselined.
Schedule buffer display | 36 | Gantt shows 36 weeks. If tasks extend past week 36, extend the displayed columns.
Dates recalculated |  | Finish date stays blank until an approved kickoff is entered.
How to use |  | Start on AWS start: provision EC2, download Qwen3.5-4B and run text/image inference. The AWS starter ZIP supplies reference scripts. Detailed format recipes follow in the runbook.
Tasks |  | Edit amber task inputs for estimated duration, baseline hold day, predecessor IDs, effort, status and progress. Calculated dates and Gantt update. One day is a working day.
Baseline logic |  | All predecessors are finish-to-start plus one working day. Baseline hold days include initial daily resource leveling. They are not promised dates.
Resource availability |  | The initial schedule assumes a maximum 8 h/day per role and 24 h/day for a pooled expert/reviewer team. Confirm those peak reservations at mobilization.
After edits |  | Dependencies recalculate, but resource leveling does not rerun automatically. Check Capacity and Weekly effort and move hold days to resolve conflicts. Holidays and absence calendars require a schedule update.
Task detail |  | Inputs, steps, deliverable and acceptance check define completion. Paste evidence or blocker references in Tasks. A date passing never marks work complete.
Source routing |  | All 51 prior source leads are mapped. Model weights, tool software, documents, datasets and catalog leads follow different routes. No source has been newly ingested by this plan.
Formats |  | Raw PDF/DOCX/EML/audio/images become reviewed evidence JSONL. Retrieval gets chunks and vectors. SFT gets prompt/completion JSONL plus local images decoded by the loader.
Model setup |  | Download a pinned Hugging Face model snapshot separately from data. Prove processor, mixed batches, loss masks, adapter updates and save/reload before substantive training.
Budget |  | Task hours are bottom-up execution/review estimates, not full payroll cost. Capacity planning-hour inputs preserve the earlier envelope. Unassigned hours cover overhead and uncertainty, not automatically savings.
Release boundary |  | Internal refining pilot only. Rights, technical acceptance and security acceptance are prerequisites. Expert candidates and licensing are unconfirmed.
Legend |  | Amber = editable planning input. Blue Gantt bar = scheduled task. Darker bar = decision gate. Initial progress is zero. Original documents remain unchanged.

## Gantt
Implementation Gantt
Relative weeks. Set kickoff on Start here for calendar dates. Planned bars are not completion claims.
ID | Task | Owner | Start week | Finish week | Status | Complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
B01 | Launch AWS GPU workspace and private S3 stores | OPS | 1 | 1 | Not started | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B02 | Prepare PyTorch environment on AWS GPU host | AI | 1 | 1 | Not started | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B03 | Pin the Hugging Face foundation model revision | HP | 1 | 1 | Not started | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B04 | Download Qwen3.5 weights into AWS and archive in S3 | AI | 2 | 2 | Not started | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B05 | Run the foundation model in AWS on text and images | AI | 2 | 2 | Not started | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B06 | Inspect adapter targets and loss masking | AI | 2 | 3 | Not started | 0% | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B07 | Prove train save reload compatibility | AI | 3 | 3 | Not started | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A01 | Define three pilot workflows | HP | 1 | 1 | Not started | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A02 | Assign named delivery and review owners | MD | 1 | 1 | Not started | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A03 | Measure current engineering workflow | CD | 1 | 2 | Not started | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A04 | Normalize all existing source leads | KE | 1 | 1 | Not started | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A05 | Approve rights and data-use contract fields | MD | 1 | 2 | Not started | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A06 | Approve hosting and access architecture | SEC | 1 | 2 | Not started | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A07 | Create annotation and acceptance rubrics | TD | 1 | 2 | Not started | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G0 | G0 authorize baseline work | MD | 2 | 2 | Not started | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C01 | Build intake manifest and quarantine handler | AI | 3 | 4 | Not started | 0% | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C02 | Acquire first cleared document sample | KE | 3 | 4 | Not started | 0% | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C03 | Implement digital PDF and HTML extraction | AI | 4 | 4 | Not started | 0% | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C04 | Implement scan OCR and image extraction | OPS | 4 | 5 | Not started | 0% | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C05 | Implement Word and slide extraction | KE | 5 | 5 | Not started | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C06 | Implement engineering image annotation | PAE | 6 | 7 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C07 | Implement email thread normalization | KE | 6 | 6 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C08 | Implement tabular operating-data conversion | PAE | 6 | 6 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09 | Implement interview transcription route | KE | 6 | 7 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C10 | Normalize text tables equations and units | PAE | 7 | 8 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C11 | Add deduplication and case-family grouping | AI | 6 | 7 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C12 | Create batch audit and retry controls | OPS | 8 | 8 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D01 | Author first original expert cases | KE | 4 | 5 | Not started | 0% | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D02 | Freeze initial family splits | TD | 7 | 7 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D03 | Build first 400 reviewed SFT examples | KE | 9 | 10 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D04 | Build baseline development questions | TD | 7 | 8 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E01 | Build evidence chunks and citation mapping | AI | 8 | 9 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E02 | Load lexical and vector retrieval index | AI | 9 | 9 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E03 | Create first validated calculation tools | PAE | 4 | 5 | Not started | 0% | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1 | G1 accept working baseline | HP | 10 | 10 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E04 | Benchmark retrieval and tune chunk policy | AI | 10 | 11 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E05 | Add reranker and evidence packaging | AI | 11 | 11 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E06 | Test revocation and index versioning | OPS | 11 | 12 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F01 | Compare text OCR and native vision | TD | 10 | 11 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F02 | Decide model and visual scope | HP | 12 | 12 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2 | G2 authorize adaptation tranche | MD | 12 | 12 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D05 | Acquire and admit production source batches | KE | 10 | 15 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D06 | Expand and reconcile 300 case families | KE | 15 | 19 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D07 | Author remaining 1600 examples | KE | 19 | 21 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D08 | Build full development and locked suites | TD | 19 | 21 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09 | Audit data rights lineage and contamination | KE | 21 | 22 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D10 | Package portable SFT datasets | AI | 22 | 22 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F03 | Implement processor and token preflight | AI | 13 | 13 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F04 | Set training configuration and tracking | HP | 14 | 14 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F05 | Run pilot adapter learning curve | AI | 14 | 15 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F06 | Tune bounded development configurations | AI | 17 | 20 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F07 | Train final adapter and seed repeats | AI | 22 | 23 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F08 | Export reload and compare tuned candidate | AI | 23 | 23 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3 | G3 freeze release candidate | HP | 23 | 23 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H01 | Build internal evidence review interface | OPS | 13 | 14 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H02 | Build inference and tool service | AI | 15 | 17 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H03 | Integrate serving adapter and processor | AI | 23 | 24 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H04 | Build monitoring and controlled feedback queue | OPS | 17 | 19 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I01 | Run locked independent technical evaluation | TD | 24 | 25 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I02 | Run challenge and security tests | SEC | 24 | 25 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I03 | Measure workload and reviewer efficiency | HP | 24 | 25 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I04 | Remediate and prepare fresh evaluation cases | AI | 25 | 26 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I05 | Test backup restore and rollback | OPS | 24 | 25 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I06 | Sign technical security and release records | HP | 26 | 27 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4 | G4 authorize supervised internal pilot | MD | 27 | 27 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J01 | Onboard ten internal pilot users | CD | 27 | 28 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J02 | Run supervised briefs and weekly reviews | PAE | 28 | 30 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
J03 | Measure pilot value and operating cost | HP | 28 | 28 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J04 | Prepare continuation and next backlog | MD | 31 | 31 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
G5 | G5 decide continuation | MD | 31 | 31 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0

## Tasks
Implementation tasks
Amber fields are editable. Start and finish are formulas. Owner and reviewer codes are defined in Capacity.
ID | Workstream | Task | Owner code | Baseline hold day | Duration days | Predecessor1 | Predecessor2 | Predecessor3 | Predecessor4 | Start day | Finish day | Start date | Finish date | Owner hours | Reviewer code | Review hours | Status | Complete | Runbook section | Blocker or evidence
B01 | Environment | Launch AWS GPU workspace and private S3 stores | OPS | 1 | 3 |  |  |  |  | 1 | 3 |  |  | 20 | SEC | 6 | Not started | 0% | 2
B02 | Environment | Prepare PyTorch environment on AWS GPU host | AI | 4 | 2 | B01 |  |  |  | 4 | 5 |  |  | 12 | OPS | 4 | Not started | 0% | 12
B03 | Environment | Pin the Hugging Face foundation model revision | HP | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 4 | SEC | 3 | Not started | 0% | 12
B04 | Environment | Download Qwen3.5 weights into AWS and archive in S3 | AI | 6 | 1 | B01 | B02 | B03 |  | 6 | 6 |  |  | 6 | OPS | 3 | Not started | 0% | 12
B05 | Environment | Run the foundation model in AWS on text and images | AI | 7 | 2 | B04 |  |  |  | 7 | 8 |  |  | 12 | HP | 4 | Not started | 0% | 12
B06 | Environment | Inspect adapter targets and loss masking | AI | 9 | 3 | B05 |  |  |  | 9 | 11 |  |  | 20 | OPS | 6 | Not started | 0% | 14
B07 | Environment | Prove train save reload compatibility | AI | 12 | 3 | B06 |  |  |  | 12 | 14 |  |  | 18 | HP | 4 | Not started | 0% | 14
A01 | Mobilize | Define three pilot workflows | HP | 2 | 2 |  |  |  |  | 2 | 3 |  |  | 12 | TD | 2 | Not started | 0% | 1
A02 | Mobilize | Assign named delivery and review owners | MD | 1 | 3 |  |  |  |  | 1 | 3 |  |  | 10 | HP | 2 | Not started | 0% | 1
A03 | Mobilize | Measure current engineering workflow | CD | 4 | 4 | A01 |  |  |  | 4 | 7 |  |  | 24 | HP | 4 | Not started | 0% | 18
A04 | Mobilize | Normalize all existing source leads | KE | 2 | 3 |  |  |  |  | 2 | 4 |  |  | 18 | MD | 3 | Not started | 0% | 3
A05 | Mobilize | Approve rights and data-use contract fields | MD | 5 | 5 | A04 |  |  |  | 5 | 9 |  |  | 20 | SEC | 8 | Not started | 0% | 3
A06 | Mobilize | Approve hosting and access architecture | SEC | 4 | 5 | A01 | A02 |  |  | 4 | 8 |  |  | 24 | HP | 4 | Not started | 0% | 2
A07 | Mobilize | Create annotation and acceptance rubrics | TD | 4 | 5 | A01 | A02 |  |  | 4 | 8 |  |  | 24 | EXP | 8 | Not started | 0% | 8
G0 | Gate | G0 authorize baseline work | MD | 10 | 1 | A03 | A05 | A06 | A07 | 10 | 10 |  |  | 4 | HP | 2 | Not started | 0% | 1
C01 | Intake | Build intake manifest and quarantine handler | AI | 15 | 3 | B01 | A05 | G0 |  | 15 | 17 |  |  | 18 | SEC | 4 | Not started | 0% | 4
C02 | Intake | Acquire first cleared document sample | KE | 14 | 3 | B01 | A05 | G0 |  | 14 | 16 |  |  | 16 | MD | 3 | Not started | 0% | 3
C03 | Intake | Implement digital PDF and HTML extraction | AI | 18 | 3 | C01 | C02 |  |  | 18 | 20 |  |  | 20 | KE | 6 | Not started | 0% | 5
C04 | Intake | Implement scan OCR and image extraction | OPS | 18 | 4 | C01 | C02 |  |  | 18 | 21 |  |  | 24 | PAE | 8 | Not started | 0% | 5
C05 | Intake | Implement Word and slide extraction | KE | 23 | 3 | C01 |  |  |  | 23 | 25 |  |  | 16 | PAE | 4 | Not started | 0% | 6
C06 | Intake | Implement engineering image annotation | PAE | 30 | 5 | C04 | A07 |  |  | 30 | 34 |  |  | 28 | EXP | 12 | Not started | 0% | 7
C07 | Intake | Implement email thread normalization | KE | 26 | 4 | C01 | A05 |  |  | 26 | 29 |  |  | 20 | SEC | 5 | Not started | 0% | 6
C08 | Intake | Implement tabular operating-data conversion | PAE | 26 | 4 | C01 |  |  |  | 26 | 29 |  |  | 24 | EXP | 6 | Not started | 0% | 7
C09 | Intake | Implement interview transcription route | KE | 30 | 4 | C01 | A05 |  |  | 30 | 33 |  |  | 20 | EXP | 10 | Not started | 0% | 6
C10 | Intake | Normalize text tables equations and units | PAE | 35 | 4 | C03 | C04 | C05 | C08 | 35 | 38 |  |  | 22 | EXP | 8 | Not started | 0% | 8
C11 | Intake | Add deduplication and case-family grouping | AI | 30 | 3 | C03 | C04 | C07 |  | 30 | 32 |  |  | 16 | KE | 6 | Not started | 0% | 8
C12 | Intake | Create batch audit and retry controls | OPS | 39 | 2 | C10 | C11 |  |  | 39 | 40 |  |  | 10 | AI | 3 | Not started | 0% | 4
D01 | Curation | Author first original expert cases | KE | 17 | 6 | C02 | A07 |  |  | 17 | 22 |  |  | 32 | EXP | 24 | Not started | 0% | 9
D02 | Curation | Freeze initial family splits | TD | 33 | 2 | D01 | C11 |  |  | 33 | 34 |  |  | 12 | EXP | 8 | Not started | 0% | 9
D03 | Curation | Build first 400 reviewed SFT examples | KE | 42 | 5 | D02 | C10 | C06 |  | 42 | 46 |  |  | 40 | EXP | 50 | Not started | 0% | 10
D04 | Curation | Build baseline development questions | TD | 35 | 4 | D02 |  |  |  | 35 | 38 |  |  | 18 | EXP | 16 | Not started | 0% | 16
E01 | Retrieval | Build evidence chunks and citation mapping | AI | 39 | 3 | C03 | C06 | C10 |  | 39 | 41 |  |  | 18 | KE | 5 | Not started | 0% | 11
E02 | Retrieval | Load lexical and vector retrieval index | AI | 42 | 3 | E01 | B04 |  |  | 42 | 44 |  |  | 18 | SEC | 5 | Not started | 0% | 11
E03 | Retrieval | Create first validated calculation tools | PAE | 18 | 8 | A07 | B01 |  |  | 18 | 25 |  |  | 40 | EXP | 16 | Not started | 0% | 11
G1 | Gate | G1 accept working baseline | HP | 47 | 1 | B07 | D03 | D04 | E02 | 47 | 47 |  |  | 4 | TD | 4 | Not started | 0% | 1
E04 | Retrieval | Benchmark retrieval and tune chunk policy | AI | 48 | 4 | G1 | E03 |  |  | 48 | 51 |  |  | 24 | PAE | 6 | Not started | 0% | 11
E05 | Retrieval | Add reranker and evidence packaging | AI | 52 | 3 | E04 |  |  |  | 52 | 54 |  |  | 16 | SEC | 4 | Not started | 0% | 11
E06 | Retrieval | Test revocation and index versioning | OPS | 55 | 3 | E05 |  |  |  | 55 | 57 |  |  | 16 | SEC | 5 | Not started | 0% | 11
F01 | Baseline | Compare text OCR and native vision | TD | 48 | 7 | G1 | E03 |  |  | 48 | 54 |  |  | 24 | EXP | 30 | Not started | 0% | 16
F02 | Baseline | Decide model and visual scope | HP | 58 | 2 | F01 | E05 | E06 |  | 58 | 59 |  |  | 10 | TD | 4 | Not started | 0% | 16
G2 | Gate | G2 authorize adaptation tranche | MD | 60 | 1 | F02 | E06 |  |  | 60 | 60 |  |  | 4 | HP | 3 | Not started | 0% | 1
D05 | Curation | Acquire and admit production source batches | KE | 48 | 25 | G1 |  |  |  | 48 | 72 |  |  | 80 | MD | 12 | Not started | 0% | 3
D06 | Curation | Expand and reconcile 300 case families | KE | 73 | 20 | G2 | D05 |  |  | 73 | 92 |  |  | 90 | EXP | 60 | Not started | 0% | 9
D07 | Curation | Author remaining 1600 examples | KE | 93 | 12 | D06 |  |  |  | 93 | 104 |  |  | 90 | EXP | 160 | Not started | 0% | 10
D08 | Curation | Build full development and locked suites | TD | 93 | 10 | D06 |  |  |  | 93 | 102 |  |  | 40 | EXP | 80 | Not started | 0% | 16
D09 | Curation | Audit data rights lineage and contamination | KE | 105 | 3 | D07 | D08 |  |  | 105 | 107 |  |  | 22 | SEC | 6 | Not started | 0% | 9
D10 | Curation | Package portable SFT datasets | AI | 108 | 2 | D09 |  |  |  | 108 | 109 |  |  | 14 | KE | 4 | Not started | 0% | 10
F03 | Training | Implement processor and token preflight | AI | 61 | 5 | G2 | B07 |  |  | 61 | 65 |  |  | 26 | OPS | 8 | Not started | 0% | 13
F04 | Training | Set training configuration and tracking | HP | 66 | 3 | F03 |  |  |  | 66 | 68 |  |  | 14 | AI | 4 | Not started | 0% | 14
F05 | Training | Run pilot adapter learning curve | AI | 69 | 6 | F04 | D03 |  |  | 69 | 74 |  |  | 30 | TD | 8 | Not started | 0% | 14
F06 | Training | Tune bounded development configurations | AI | 85 | 12 | F05 |  |  |  | 85 | 96 |  |  | 52 | HP | 8 | Not started | 0% | 14
F07 | Training | Train final adapter and seed repeats | AI | 110 | 3 | D10 | F06 |  |  | 110 | 112 |  |  | 20 | TD | 6 | Not started | 0% | 14
F08 | Training | Export reload and compare tuned candidate | AI | 113 | 1 | F07 |  |  |  | 113 | 113 |  |  | 8 | HP | 3 | Not started | 0% | 15
G3 | Gate | G3 freeze release candidate | HP | 114 | 1 | F08 | D08 | D09 |  | 114 | 114 |  |  | 4 | TD | 3 | Not started | 0% | 1
H01 | Application | Build internal evidence review interface | OPS | 61 | 10 | G2 | E05 |  |  | 61 | 70 |  |  | 50 | PAE | 8 | Not started | 0% | 17
H02 | Application | Build inference and tool service | AI | 75 | 10 | H01 | E03 |  |  | 75 | 84 |  |  | 40 | SEC | 10 | Not started | 0% | 15
H03 | Application | Integrate serving adapter and processor | AI | 115 | 4 | G3 | H02 |  |  | 115 | 118 |  |  | 22 | OPS | 6 | Not started | 0% | 15
H04 | Application | Build monitoring and controlled feedback queue | OPS | 85 | 8 | H02 |  |  |  | 85 | 92 |  |  | 36 | SEC | 6 | Not started | 0% | 17
I01 | Evaluation | Run locked independent technical evaluation | TD | 119 | 5 | H03 | D08 |  |  | 119 | 123 |  |  | 28 | EXP | 60 | Not started | 0% | 16
I02 | Evaluation | Run challenge and security tests | SEC | 119 | 5 | H03 | D08 |  |  | 119 | 123 |  |  | 28 | OPS | 10 | Not started | 0% | 17
I03 | Evaluation | Measure workload and reviewer efficiency | HP | 119 | 5 | H03 | A03 |  |  | 119 | 123 |  |  | 20 | CD | 8 | Not started | 0% | 16
I04 | Evaluation | Remediate and prepare fresh evaluation cases | AI | 124 | 6 | I01 | I02 | I03 |  | 124 | 129 |  |  | 30 | EXP | 30 | Not started | 0% | 16
I05 | Evaluation | Test backup restore and rollback | OPS | 119 | 4 | H03 | H04 |  |  | 119 | 122 |  |  | 20 | SEC | 5 | Not started | 0% | 17
I06 | Evaluation | Sign technical security and release records | HP | 130 | 3 | I04 | I05 |  |  | 130 | 132 |  |  | 10 | TD | 4 | Not started | 0% | 17
G4 | Gate | G4 authorize supervised internal pilot | MD | 133 | 1 | I06 |  |  |  | 133 | 133 |  |  | 4 | HP | 2 | Not started | 0% | 1
J01 | Pilot | Onboard ten internal pilot users | CD | 134 | 3 | G4 |  |  |  | 134 | 136 |  |  | 18 | TD | 4 | Not started | 0% | 18
J02 | Pilot | Run supervised briefs and weekly reviews | PAE | 137 | 14 | J01 |  |  |  | 137 | 150 |  |  | 90 | EXP | 80 | Not started | 0% | 18
J03 | Pilot | Measure pilot value and operating cost | HP | 137 | 4 | J01 |  |  |  | 137 | 140 |  |  | 20 | CD | 8 | Not started | 0% | 18
J04 | Pilot | Prepare continuation and next backlog | MD | 151 | 1 | J02 | J03 |  |  | 151 | 151 |  |  | 6 | TD | 3 | Not started | 0% | 18
G5 | Gate | G5 decide continuation | MD | 152 | 1 | J04 |  |  |  | 152 | 152 |  |  | 4 | HP | 2 | Not started | 0% | 1
Formulas:
Start date = IF('Start here'!$B5="","",WORKDAY('Start here'!$B5-1,[Start day]))
Finish date = IF('Start here'!$B5="","",WORKDAY('Start here'!$B5-1,[Finish day]))

## Task detail
Task procedures and acceptance
Follow the row identified in Tasks. Deliverables are required implementation outputs, not files already produced.
ID | Task | Inputs | Implementation steps | Required output | Acceptance check | Reviewer | Runbook section
B01 | Launch AWS GPU workspace and private S3 stores | Existing authorized AWS sandbox, region, network and spend envelope | Follow AWS 2: choose g6e.2xlarge and a compatible PyTorch GPU DLAMI; attach encrypted 300 GiB gp3 EBS; use Session Manager and an instance role; create private versioned S3 model, data, run and evaluator stores; record resource IDs. Use only public model weights and synthetic fixtures until G0. | aws_environment.json, GPU host and S3 inventory | Session Manager works; nvidia-smi detects one L40S; S3 role tests pass; evaluator bucket is denied to trainer. Account/quota/network access confirmed before day 1. | Parent security lead | 2
B02 | Prepare PyTorch environment on AWS GPU host | AWS GPU host and DLAMI PyTorch environment | Follow AWS 3: activate the AMI PyTorch environment, create an isolated overlay, keep the AMI CUDA/PyTorch stack, install model libraries, run pip check and CUDA/BF16 checks. Save AMI, driver, Python and package inventory. | candidate-requirements.txt and environment report | Imports and GPU/BF16 checks succeed; exact versions or Git commits captured. | Contracted implementation specialist | 12
B03 | Pin the Hugging Face foundation model revision | Qwen/Qwen3.5-4B model card and Apache-2.0 license | Choose the post-trained image/text checkpoint as the starting foundation. Resolve and save its full repository SHA and license evidence. Other candidates remain comparison options; pin embeddings separately when building retrieval. | foundation_revision.json | Exact model revision and license recorded; no floating model revision in subsequent runs. | Parent security lead | 12
B04 | Download Qwen3.5 weights into AWS and archive in S3 | AWS environment, pinned foundation revision and aws_start scripts | Run foundation_download.py on EC2 using the reviewed revision. Download safetensors, tokenizer, processor and config files to /srv/broadbridge/models; verify shards; hash all artifacts; copy the immutable revision folder to the private S3 model bucket. See AWS 3. | Local model snapshot, SHA256 manifest and private S3 copy | All weight shards and model/processor files exist; S3 copy count and sampled hashes reconcile; no proprietary source data sent to Hugging Face. | Contracted implementation specialist | 12
B05 | Run the foundation model in AWS on text and images | Pinned model and synthetic fixtures | Run foundation_smoke.py with the local model snapshot and synthetic chart. Record text and image answers, memory and timing. Extend check to ordered two-image input and empty image list. Archive baseline outputs in S3. See AWS 4. | baseline_smoke.json and compatibility_report.json | No missing architecture or image-token errors; save peak memory and latency. | Head of Product and AI | 12
B06 | Inspect adapter targets and loss masking | Loaded model named modules and collator | Select explicit language-layer projections; exclude visual encoder and projector; inspect one mixed batch and all label masks. | target_modules.txt and mask_report.json | Only intended LoRA weights are trainable; prompt/image/padding tokens have no supervised loss. | Contracted implementation specialist | 14
B07 | Prove train save reload compatibility | Two approved or synthetic examples | Run ten optimizer steps on a fixture; save adapter and processor; reload with exact base; compare deterministic logits within agreed tolerance. | smoke adapter and reload_report.json | Finite loss, gradient updates, successful reload and reproducible outputs. Fixture is excluded from production data. | Head of Product and AI | 14
A01 | Define three pilot workflows | CTO plan and refining scope | Specify evidence review, diagnostic brief and calculation support; list allowed users and excluded operating actions. | charter.md and workflow list | Technical Director accepts scope and prohibited actions. | Technical Director | 1
A02 | Assign named delivery and review owners | Seven-role organization and contracted support | Protect the role hours; appoint separate content authors and reviewers; reserve parent security capacity. | staffing.csv and reviewer roster | Named owner and independent reviewer for each workstream. | Head of Product and AI | 1
A03 | Measure current engineering workflow | Representative internal engineering questions | Time at least ten manually prepared briefs; record complexity, corrections and acceptance rubric before tool use. | baseline_effort.csv | Baseline includes review time and task mix; no fabricated ROI. | Head of Product and AI | 18
A04 | Normalize all existing source leads | 32 general and 19 Norm source-register rows | Retain original IDs; distinguish models, software, data, articles and catalogs; assign processing recipe and priority. | source_register.csv | All 51 prior rows mapped; catalogs remain acquisition leads. | Managing Director | 3
A05 | Approve rights and data-use contract fields | Candidate source terms and intended internal use | Record acquisition, OCR, retrieval, SFT, evaluation, processor, retention and derived-weight permissions separately; resolve publisher and former-client rights. | rights_ledger.jsonl and grant templates | Every admitted use has evidence; unknown permissions remain held. | Parent security lead | 3
A06 | Approve hosting and access architecture | Data classes and expected GPU capacity | Choose region and processors; separate quarantine, retrieval, training and evaluator identities; allow model-download egress only. | environment_design.md | Evaluator answer store cannot be read by trainer or production retriever. | Head of Product and AI | 2
A07 | Create annotation and acceptance rubrics | Launch questions and expert availability | Define factual, visual, numeric and missing-evidence rubrics; fix critical-error definitions and review rules. | rubrics_v1.json | Two reviewers agree on trial labels and adjudication method. | Contracted expert or independent reviewer | 8
G0 | G0 authorize baseline work | Charter, rights route, staffing and environment design | Record scope, spend limit, named owners and unresolved source holds. | gate_G0.json | Only cleared sources and approved environment may enter baseline work. | Head of Product and AI | 1
C01 | Build intake manifest and quarantine handler | Authorized source files and grants | Compute asset SHA256, sniff MIME, scan in isolation, block macros, assign source and family IDs, record custody and parent attachments. | intake_manifest.jsonl | Repeated intake is idempotent; rejected or held assets cannot advance. | Parent security lead | 4
C02 | Acquire first cleared document sample | P01 P02 and authorized original expert sample | Obtain exact official editions or authorized files; retain URL/date/edition and item-level notices; admit only cleared uses. | initial raw batch and grant records | Full documents present; no preview or search snippet presented as a complete work. | Managing Director | 3
C03 | Implement digital PDF and HTML extraction | Cleared digital PDF or HTML sample | Use Docling or equivalent pinned parser; retain page/heading coordinates, table cells and captions; save JSON and Markdown views. | documents.jsonl and figures | Reading order and page coverage checked against originals. | Knowledge Engineer | 5
C04 | Implement scan OCR and image extraction | Scanned pages and engineering figure sample | Render lossless page images near 300 dpi; orient/deskew a derivative; OCR; preserve original coordinates and transforms. | page PNGs, regions.jsonl and OCR flags | All critical values, units, subscripts and arrows independently checked; unreadable fields stay unknown. | Process Applications Engineer | 5
C05 | Implement Word and slide extraction | Authorized DOCX and PPTX work papers | Extract paragraphs, tables, notes and image anchors; record revisions and slide IDs; do not accept tracked changes silently. | normalized work-paper records | Comments, notes and revisions are explicitly included or excluded by rule. | Process Applications Engineer | 6
C06 | Implement engineering image annotation | Approved PFD, P&ID, sketch and trend examples | Create overview plus bounded crops; label legibility, tags, units, values, arrows and connections; attach caption and scope. | visual_labels.jsonl | No inferred hidden connectivity; every label points to a visible region. | Contracted expert or independent reviewer | 7
C07 | Implement email thread normalization | Authorized EML or MBOX export and attachments | Preserve Message-ID, replies, timezones and attachment relationships; deduplicate quotes; redact identities; separate question-time facts from later outcomes. | threads.jsonl and attachment manifest | Chronology retained; replies and third-party attachments receive separate permission review. | Parent security lead | 6
C08 | Implement tabular operating-data conversion | Authorized CSV XLSX or historian export | Export values with units, timestamps, timezone and quality flags; preserve original formulas; distinguish gauge/absolute pressure and missing readings. | measurements.parquet and data_dictionary.json | Sampled values reconcile to original; no silent interpolation or unit conversion. | Contracted expert or independent reviewer | 7
C09 | Implement interview transcription route | Consented WAV MP3 MP4 interview sample | Create timestamped transcript and speaker labels; verify technical terms with expert; select only instructional frames; link all derivatives to source time. | segments.jsonl, transcript and selected PNGs | Expert approves technical transcript; separate grants for recording, slides and reuse. | Contracted expert or independent reviewer | 6
C10 | Normalize text tables equations and units | Extracted documents and measurements | Normalize Unicode and whitespace conservatively; keep raw text; represent tables with row/column headers and equations with variable definitions. | canonical evidence records | Decimal signs, inequalities, exponents, units and footnotes reconcile; failed regions quarantined. | Contracted expert or independent reviewer | 8
C11 | Add deduplication and case-family grouping | Asset hashes, text and attachment links | Detect exact duplicates and near duplicates; group republished articles, revisions, email replies, crops and synthetic variants into one family. | family_manifest.jsonl | Known duplicate pairs stay together; similarity hits reviewed rather than deleted blindly. | Knowledge Engineer | 8
C12 | Create batch audit and retry controls | Extraction results and failures | Record parser/model revision, state, failure reason and output hashes; retry only changed or failed assets; keep held rows out of downstream exports. | batch_audit.jsonl and rejection queue | Reprocessing unchanged input produces no duplicate evidence or training records. | Applied AI Engineer | 4
D01 | Author first original expert cases | Cleared expert interviews or authored notes | Capture symptom, regime, question-time evidence, alternatives, discriminating checks, outcome and limitations; get author sign-off. | case packets batch 1 | No client identifiers or restricted source text without explicit clearance. | Contracted expert or independent reviewer | 9
D02 | Freeze initial family splits | Family manifest and case inventory | Assign families to train/dev/test before variants; allocate evaluator-only answer access; tag all child assets with inherited split. | split_manifest_v1.jsonl | No family crosses splits; test-family answers absent from trainer and retrieval. | Contracted expert or independent reviewer | 9
D03 | Build first 400 reviewed SFT examples | Training families and structured evidence | Write 300 text and 100 visual prompt/completion records; attach evidence; check answer visibility and reviewer provenance. | train_v0.jsonl and linked PNGs | 400 accepted records; every image resolves and every answer has review evidence. | Contracted expert or independent reviewer | 10
D04 | Build baseline development questions | Development families and rubric | Create tasks from 20 dev families; separate prompts, references and scoring keys; ensure visual/text paired comparisons. | dev_v0 and gold answers | No development example enters SFT; task mix documented. | Contracted expert or independent reviewer | 16
E01 | Build evidence chunks and citation mapping | Canonical cleared evidence | Split by section at proposed 400-800 tokenizer tokens; retain table/caption integrity, parent references, page regions, family and access metadata. | chunks.jsonl | Every chunk resolves to an authorized original and has deterministic ID. | Knowledge Engineer | 11
E02 | Load lexical and vector retrieval index | Approved chunks and pinned embedding model | Download and hash pinned Qwen3-Embedding-0.6B and Qwen3-Reranker-0.6B snapshots to AWS. Embed approved text; store vectors with model revision/dimension; create lexical index; apply access and split filters before candidates. | retrieval index v0 | Known positives retrievable and unauthorized or test-answer chunks excluded. | Parent security lead | 11
E03 | Create first validated calculation tools | Selected property and unit operations | Implement typed unit conversion and one bounded balance/property tool; validate independent values and out-of-range errors; record tool version. | tool schemas and reference fixtures | Golden values within preset tolerance; wrong units and unsupported fluids rejected. | Contracted expert or independent reviewer | 11
G1 | G1 accept working baseline | First 400 examples, compatibility report and evidence index | Review baseline readiness and checked tool availability; approve paired vision benchmark. | gate_G1.json | Model loads/trains/reloads; corpus and test segregation work; E03 completed. | Technical Director | 1
E04 | Benchmark retrieval and tune chunk policy | Engineer-labeled evidence queries | Measure recall at 20 candidates; test 400/600/800 token chunks and overlaps on dev data; use same settings across model comparisons. | retrieval_eval.csv and frozen policy | Proposed 90% recall@20 target assessed with denominators; missing evidence investigated. | Process Applications Engineer | 11
E05 | Add reranker and evidence packaging | Permitted retrieval candidates and M06 | Rerank only authorized candidates; select top evidence within token budget; retain image region links and cited IDs. | context_pack schema and baseline | Citations resolve; forbidden candidates cannot enter reranker or output. | Parent security lead | 11
E06 | Test revocation and index versioning | Grant expiry fixture and indexed copies | Revoke one source; remove text, vectors, images and cached contexts; verify old release is not served to unauthorized users. | revocation_report.json | Zero retrieval hits or cache leaks from revoked grant under tested identities. | Parent security lead | 11
F01 | Compare text OCR and native vision | Paired development questions and untuned models | Run Qwen3-8B text, Qwen3.5 text/OCR and Qwen3.5 image paths with identical evidence and tools; blind and counterbalance review. | baseline_predictions.jsonl and paired scores | Record quality, critical errors, timing, GPU memory and cost; isolate image contribution. | Contracted expert or independent reviewer | 16
F02 | Decide model and visual scope | Paired results and compatibility evidence | Retain native vision only with supported quality or review-time gain; record selected model revision, accepted visual types and fallback. | architecture_decision.md | Five-point acceptance or 15% review-time improvement is supported; inconclusive results narrow scope. | Technical Director | 16
G2 | G2 authorize adaptation tranche | Architecture decision and refreshed forecast | Approve remaining spend and exact selected scope; defer unsupported image tasks. | gate_G2.json | Rights, staffing and evidence justify continuation. | Head of Product and AI | 1
D05 | Acquire and admit production source batches | Prioritized cleared source list | Process launch documents and expert packets in weekly batches; follow the source routing sheet; keep excluded datasets out. | weekly intake batches | Coverage grows without converting catalog leads or uncleared previews into content. | Managing Director | 3
D06 | Expand and reconcile 300 case families | Accepted evidence and expert-authored incidents | Assemble 180 train, 60 dev and 60 test families; track equipment and visual coverage; keep scenario variants within parent family. | family_manifest_v2.jsonl | 300 independent families supported by provenance; at least 90 train and 30 each dev/test have usable visual evidence. | Contracted expert or independent reviewer | 9
D07 | Author remaining 1600 examples | Approved training families | Add 1200 text and 400 image/text records to initial batch; follow diagnostic, clarification, tool, grounding and escalation quotas. | train_v1.jsonl | Final 1500 text and 500 visual examples; every answer has evidence and independent review. | Contracted expert or independent reviewer | 10
D08 | Build full development and locked suites | 60 dev families and 60 locked test families | Create 120 locked case tasks and 180 challenge prompts; keep gold evaluator-only; tag task subtype and tolerances. | dev_v1 and sealed test v1 | Test suite families disjoint; challenge prompts distinguished from independent incidents. | Contracted expert or independent reviewer | 16
D09 | Audit data rights lineage and contamination | Final manifests and all derivative IDs | Check grants, review states, exact/near duplicates and answer phrases against retrieval and prompts; trace teacher generation sources. | dataset_audit.json and release manifest | No unauthorized use or cross-split family; rejected records listed with reason. | Parent security lead | 9
D10 | Package portable SFT datasets | Accepted JSONL and local images | Validate schema, materialize image paths, create Hugging Face runtime rows; strip governance metadata from model inputs; hash export. | train/dev release and dataset_card.md | Images and placeholders match; no remote URL fetch; frozen test data not mounted on training host. | Knowledge Engineer | 10
F03 | Implement processor and token preflight | Selected model processor and pilot examples | Use shipped chat template; check prefix masks and image tokens; count full processed length; reject records beyond 8192-token proposal. | preflight_report.json | No silent truncation; supervised labels only on approved answer tokens. | Contracted implementation specialist | 13
F04 | Set training configuration and tracking | Train compatibility and memory profile | Start BF16 LoRA rank 16, alpha 32, one epoch, LR5e-5; freeze visual encoder; set batch 1 accumulation 16 seed 17 and spend limit. | run_config.json and run tracker | Config includes base/processor/data hashes, explicit module list and observed effective batch. | Applied AI Engineer | 14
F05 | Run pilot adapter learning curve | First approved 400 examples and dev set | Train on 100/200/400 record subsets grouped by family; compare held-out dev quality and runtime; inspect failures and memorized passages. | learning_curve.csv and pilot adapters | Stop on NaN, leakage, loss-mask errors or critical regression; do not use locked tests. | Technical Director | 14
F06 | Tune bounded development configurations | Pilot findings and expanding approved data | Compare ranks 16/32 and LR5e-5/1e-4; at most eight configs per finalist; retain text-only and untuned controls. | experiment register and candidate recipe | Selection based on dev quality, effort and critical errors; not training loss alone. | Head of Product and AI | 14
F07 | Train final adapter and seed repeats | Frozen 2000-example release and selected recipe | Train selected mixed model and text-adapter control; repeat finalist seeds; preserve checkpoints and budget/quality logs. | candidate adapter and seed results | No held-out reuse; exact inputs and settings reconstruct each run. | Technical Director | 14
F08 | Export reload and compare tuned candidate | Final adapter and pinned base | Save adapter safetensors/config and processor; reload in fresh environment; compare to untuned same-input model on dev. | candidate_manifest.json and adapter report | Tuning gain meets proposal or release keeps untuned baseline; memory and latency recorded. | Head of Product and AI | 15
G3 | G3 freeze release candidate | Reproducible model, corpus, tools and development report | Freeze all release versions and commit candidate to independent evaluation. | gate_G3.json | 2000 approved examples and 300 family manifest reconcile; no open critical development defect. | Technical Director | 1
H01 | Build internal evidence review interface | Context pack and brief schema | Show source passage/image crop beside editable extracted facts and brief; capture acceptance, corrections and escalation reason. | review UI build | Reviewers can verify every cited source and correct misread values before accepting. | Process Applications Engineer | 17
H02 | Build inference and tool service | Model baseline, tool schemas and auth policy | Add bounded inference endpoint; validate structured outputs and tool calls; reject arbitrary shell/URL actions; enforce request limits. | internal service build | Permissions enforced server-side; unknown tools/units rejected; no plant-control writes. | Parent security lead | 15
H03 | Integrate serving adapter and processor | Frozen candidate and serving environment | Use supported Transformers serving first; test vLLM only if exact adapter/vision path works; compare quantized and original outputs before selection. | serving_manifest.json | Selected backend reproduces accepted answers and image preprocessing; no silent fallback to base model. | Contracted implementation specialist | 15
H04 | Build monitoring and controlled feedback queue | Review logs and retention policy | Record evidence IDs, release IDs, errors, latency and review outcomes; quarantine feedback; redact sensitive logs; implement access-aware deletion. | monitoring and feedback workflow | No online retraining; correction becomes data only after rights and expert review. | Parent security lead | 17
I01 | Run locked independent technical evaluation | Sealed 120 tasks and candidate service | Independent reviewers score blind; apply prespecified denominators, tolerances and critical-error veto; log failures by family and modality. | locked_eval_v1.jsonl | At least 85% accepted diagnostic tasks,95% grounded claims,98% critical legible values and numeric checks; no critical failures. | Contracted expert or independent reviewer | 16
I02 | Run challenge and security tests | 180 challenge prompts and access matrix | Test image/text injections, fake citations, wrong units, cross-project access, expired grants, resource exhaustion and unsafe tool requests. | security_report.json | Zero unauthorized disclosure/actions in tested cases; no unresolved high-severity finding. | Contracted implementation specialist | 17
I03 | Measure workload and reviewer efficiency | Fixed workload, baseline times and reviewers | Test five concurrent users, measured token/image budget and up to three tools; counterbalance human comparison tasks; compute per-accepted-brief cost. | performance_and_effort.csv | Report p95, rejection rate and median review effort; investigate deviations from 60-second proposal. | Commercial Director | 16
I04 | Remediate and prepare fresh evaluation cases | Failure records and independent reviewer capacity | Fix affected component; refresh holdout for material fixes exposed by locked suite; rerun targeted and critical regression tests. | remediation ledger and fresh holdout | No reuse of exposed test cases as sole proof of corrected generalization. If insufficient cases, defer gate. | Contracted expert or independent reviewer | 16
I05 | Test backup restore and rollback | Versioned candidate and backup policy | Restore sources/review records within approved recovery window; deploy previous version; revoke access and verify audit trail. | restore_rollback_report.json | Four-business-hour restore and 24-hour review-record loss objectives demonstrated or revised before approval. | Parent security lead | 17
I06 | Sign technical security and release records | Acceptance reports and resolved issue ledger | Obtain separate Technical Director and security acceptance; package user guidance, monitoring and recovery procedures. | release_manifest.json | Single product release owner has both prerequisite acceptances. | Technical Director | 17
G4 | G4 authorize supervised internal pilot | Signed release and operations readiness | Authorize only named internal users and supported tasks for four weeks. | gate_G4.json | No critical open defect; funding and reviewer coverage available. | Head of Product and AI | 1
J01 | Onboard ten internal pilot users | Approved release and user list | Train users to inspect evidence, correct units, reject unsupported answers and escalate issues; verify access groups. | onboarding records | Each user completes a supervised sample; no external access. | Technical Director | 18
J02 | Run supervised briefs and weekly reviews | Internal engineering requests | Target 100 reviewed briefs; record acceptance, corrections, time and sources; second-review weekly sample; stop affected capability on critical defect. | pilot_briefs.jsonl and weekly metrics | Every brief reviewed; limitations and incidents recorded, including refusals. | Contracted expert or independent reviewer | 18
J03 | Measure pilot value and operating cost | Reviewed brief log and cloud/reviewer costs | Compare accepted-brief effort with baseline task mix; report quality, availability, cost and uncertainty; forecast continuing service cost. | pilot_report.md | No savings claim without observed accepted quality and recorded labor. | Commercial Director | 18
J04 | Prepare continuation and next backlog | Pilot findings and risk register | Recommend continue, narrow or stop; propose next data gaps and budget; customer use remains a separate rights and product decision. | continuation_memo.md | Board receives evidence, residual limits and named owners. | Technical Director | 18
G5 | G5 decide continuation | Pilot report and continuation memo | Record continue/narrow/stop decision and release scope. | gate_G5.json | No implied commercial launch or automatic model expansion. | Head of Product and AI | 1

## Source routing
Existing source processing routes
Prior review status retained. Acquisition and permission decisions are implementation tasks.
Source ID | Source or model | Recipe | Disposition | Task IDs | Original URL | Processing status
P01 | DOE Steam Systems and Steam Sourcebook | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.energy.gov/cmei/ito/steam-systems | Not acquired or processed in this implementation task
P02 | DOE Process Heating Sourcebook | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://betterbuildingssolutioncenter.energy.gov/better-plants/process-heating | Not acquired or processed in this implementation task
P03 | DOE Pumping System Sourcebook | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://betterbuildingssolutioncenter.energy.gov/better-plants/pumps | Not acquired or processed in this implementation task
P04 | CSB BP Texas City refinery investigation | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.csb.gov/bp-america-texas-city-refinery-explosion/ | Not acquired or processed in this implementation task
P05 | EPA AP 42 Chapter 5 petroleum industry | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.epa.gov/air-emissions-factors-and-quantification/ap-42-fifth-edition-volume-i-chapter-5-petroleum-1 | Not acquired or processed in this implementation task
P06 | EIA Open Data API | R06 | Optional dated context tool; exclude from diagnostic answer labels | C08 | https://www.eia.gov/opendata/ | Not acquired or processed in this implementation task
P07 | CoolProp | R10 | Implement as checked tool, not raw document training | E03 | https://github.com/CoolProp/CoolProp | Not acquired or processed in this implementation task
P08 | IDAES Process Systems Engineering Framework | R10 | Implement as checked tool, not raw document training | E03 | https://github.com/IDAES/idaes-pse | Not acquired or processed in this implementation task
P09 | NIST Chemistry WebBook SRD 69 | R12 | Held permission review or later practice; not first refining pilot | A05 | https://webbook.nist.gov/chemistry/ | Not acquired or processed in this implementation task
P10 | Equinor Volve field dataset | R12 | Held permission review or later practice; not first refining pilot | A05 | https://www.equinor.com/energy/volve-data-sharing | Not acquired or processed in this implementation task
P11 | NETL Energy Data eXchange | R12 | Held permission review or later practice; not first refining pilot | A05 | https://edx.netl.doe.gov/ | Not acquired or processed in this implementation task
M01 | Qwen/Qwen3-8B | R09 | Candidate; pin and validate before loading | B02 B03 B04 B05 | https://huggingface.co/Qwen/Qwen3-8B | Not acquired or processed in this implementation task
M02 | Qwen/Qwen3.5-4B | R09 | Candidate; pin and validate before loading | B02 B03 B04 B05 | https://huggingface.co/Qwen/Qwen3.5-4B | Not acquired or processed in this implementation task
M03 | mistralai/Ministral-3-8B-Instruct-2512 | R09 | Candidate; pin and validate before loading | B02 B03 B04 B05 | https://huggingface.co/mistralai/Ministral-3-8B-Instruct-2512 | Not acquired or processed in this implementation task
M04 | Qwen/Qwen3-32B | R09 | Optional drafting teacher; approved inputs only; independent answer review | B02 B03 B04 B05 | https://huggingface.co/Qwen/Qwen3-32B | Not acquired or processed in this implementation task
M05 | Qwen/Qwen3-Embedding-0.6B | R09 | Candidate; pin and validate before loading | B02 B03 B04 B05 | https://huggingface.co/Qwen/Qwen3-Embedding-0.6B | Not acquired or processed in this implementation task
M06 | Qwen/Qwen3-Reranker-0.6B | R09 | Candidate; pin and validate before loading | B02 B03 B04 B05 | https://huggingface.co/Qwen/Qwen3-Reranker-0.6B | Not acquired or processed in this implementation task
M07 | PetroGPT/Llama-3-Petro-Instruct-v1 | R12 | Hold; rights or lineage unresolved; no pilot use | A05 | https://huggingface.co/PetroGPT/Llama-3-Petro-Instruct-v1 | Not acquired or processed in this implementation task
M08 | GeoGPT-Research-Project/GeoGPT-R1-Preview | R12 | Hold; rights or lineage unresolved; no pilot use | A05 | https://huggingface.co/GeoGPT-Research-Project/GeoGPT-R1-Preview | Not acquired or processed in this implementation task
M09 | AI4Chem/ChemLLM-7B-Chat | R12 | Hold; rights or lineage unresolved; no pilot use | A05 | https://huggingface.co/AI4Chem/ChemLLM-7B-Chat | Not acquired or processed in this implementation task
D01 | PetroGPT/petro-dataset-v2 | R12 | Hold or later evaluation per original register; not launch SFT | A05 D09 | https://huggingface.co/datasets/PetroGPT/petro-dataset-v2 | Not acquired or processed in this implementation task
D02 | GeoGPT-Research-Project/GeoGPT-CoT-QA | R12 | Hold or later evaluation per original register; not launch SFT | A05 D09 | https://huggingface.co/datasets/GeoGPT-Research-Project/GeoGPT-CoT-QA | Not acquired or processed in this implementation task
D03 | petra-2026/PETRA | R12 | Hold or later evaluation per original register; not launch SFT | A05 D09 | https://huggingface.co/datasets/petra-2026/PETRA | Not acquired or processed in this implementation task
D04 | my2000cup/PetroBench | R12 | Hold or later evaluation per original register; not launch SFT | A05 D09 | https://huggingface.co/datasets/my2000cup/PetroBench | Not acquired or processed in this implementation task
D05 | FormationEval original 505 question track | R12 | Hold or later evaluation per original register; not launch SFT | A05 D09 | https://github.com/AlmazErmilov/FormationEval-an-Open-Benchmark-for-Oil-Gas-Geoscience-MCQ-Evaluation | Not acquired or processed in this implementation task
D06 | MIT OpenCourseWare | R12 | Hold or later evaluation per original register; not launch SFT | A05 D09 | https://ocw.mit.edu/pages/privacy-and-terms-of-use/ | Not acquired or processed in this implementation task
K01 | Norman and Elizabeth Lieberman expertise | R07 / R03 | Original contracted cases preferred; candidate appointment only | A05 C09 D01 | https://www.lieberman-eng.com/personnel.htm | Not acquired or processed in this implementation task
K02 | Lieberman published equipment and troubleshooting works | R11 then R01 | Obtain exact licensed full work; separate expert appointment | A05 C02 D05 | https://www.sciencedirect.com/book/monograph/9780128161616/understanding-process-equipment-for-operators-and-engineers | Not acquired or processed in this implementation task
K03 | Henry Kister Distillation Diagnostics | R11 then R01 | Obtain exact licensed full work; separate expert appointment | A05 C02 D05 | https://onlinelibrary.wiley.com/doi/book/10.1002/9781119640165 | Not acquired or processed in this implementation task
K04 | PetroSkills Campbell Gas Course | R12 | Held permission review or later practice; not first refining pilot | A05 | https://www.petroskills.com/en/training/courses/gas-conditioning-and-processing-g-4~p2995 | Not acquired or processed in this implementation task
K05 | Customer incidents procedures historian and maintenance records | R04 / R06 | Site-only retrieval by default; no shared SFT without grant | A05 C07 C08 |  | Not acquired or processed in this implementation task
K06 | OEM manuals standards and customer licensed references | R01 / R05 | Licensed retrieval only unless separate training grant | A05 C03 C06 |  | Not acquired or processed in this implementation task
N01 | Ask Norm Lieberman — public blog and Q&A archive | R04 / R01 | Separate each post, correspondent and embedded asset | A05 C03 C07 | https://asknormlieberman.blogspot.com/ | Not acquired or processed in this implementation task
N02 | Understanding vacuum system performance problems | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/home/article/17228903/beyond-back-to-basics-process-principles-and-concepts-4-understanding-vacuum-system-performance-problems | Not acquired or processed in this implementation task
N03 | Understanding how distillation trays work | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/refining-processing/refining/article/17232595/understanding-how-distillation-trays-work | Not acquired or processed in this implementation task
N04 | Understanding reflux in distillation towers | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/refining-processing/article/17229143/beyond-back-to-basics-process-principles-and-concepts-2-understanding-reflux-in-distillation-towers | Not acquired or processed in this implementation task
N05 | Understanding process heat transfer | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/refining-processing/refining/article/17232705/understanding-process-heat-transfer | Not acquired or processed in this implementation task
N06 | Design, installation pitfalls appear in vac tower retrofit | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/home/article/17238317/design-installation-pitfalls-appear-in-vac-tower-retrofit | Not acquired or processed in this implementation task
N07 | Inadequate inspection cause of flawed vac tower revamp | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/home/article/17219652/inadequate-inspection-cause-of-flawed-vac-tower-revamp | Not acquired or processed in this implementation task
N08 | Basic technology can improve refinery profits | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/home/article/17211743/basic-technology-can-improve-refinery-profits | Not acquired or processed in this implementation task
N09 | Troubleshoot operation of a steam ejector vacuum system | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.hydrocarbonprocessing.com/magazine/2016/february-2016/process-engineering-and-optimization/troubleshoot-operation-of-a-steam-ejector-vacuum-system/ | Not acquired or processed in this implementation task
N10 | Performance testing: The key to successful revamps | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.hydrocarbonprocessing.com/magazine/2017/february-2017/process-optimization/performance-testing-the-key-to-successful-revamps/ | Not acquired or processed in this implementation task
N11 | (25b) Troubleshooting Distillation Problems | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://proceedings.aiche.org/conferences/aiche-spring-meeting-and-global-congress-on-process-safety/2023/proceeding/paper/25b-troubleshooting-distillation-problems | Not acquired or processed in this implementation task
N12 | Norm P. Lieberman Video Library of Troubleshooting Process Operations | R11 then R07 | License recordings, frames and quizzes separately; evaluator quizzes isolated | A05 C09 D08 | https://lieberman-eng.com/videos.htm | Not acquired or processed in this implementation task
N13 | A Working Guide to Process Equipment, fifth edition — 26-page preview | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://lieberman-eng.com/pdfs/A%20Working%20Guide%20To%20Process%20Equipment.pdf | Not acquired or processed in this implementation task
N14 | Process Improvement Engineering book catalog | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.lieberman-eng.com/books.htm | Not acquired or processed in this implementation task
N15 | Seminar Presentations | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.lieberman-eng.com/seminars.htm | Not acquired or processed in this implementation task
N16 | Sour water strippers: design and operation | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.eptq.com/articles/liebermanweb_04042013130338.pdf | Not acquired or processed in this implementation task
N17 | Troubleshooting Vacuum Systems: Steam Turbine Surface Condensers and Refinery Vacuum Towers | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.wiley-vch.de/en/areas-interest/engineering/troubleshooting-vacuum-systems-978-1-118-29034-7 | Not acquired or processed in this implementation task
N18 | Understanding, preventing corrosion in refineries | R01 | Acquire and review item rights before use | A05 C02 C03 D05 | https://www.ogj.com/refining-processing/refining/article/17222725/understanding-preventing-corrosion-in-refineries | Not acquired or processed in this implementation task
N19 | Troubleshooting steam ejectors | R11 then R01 | Acquire full exact paper/book/article; previews and catalogs are leads only | A05 C02 D05 | https://www.eptq.com/digitalPTQ/2014%20ptq%20q4/2014%20ptq%20q4_opf_files/pdfs/2014%20ptq%20q4__.pdf | Not acquired or processed in this implementation task

## Processing recipes
Processing recipes by input format
Raw formats are preserved; reviewed derivatives are routed separately to retrieval, training and evaluation.
Recipe | Input type | Accepted source formats | Processing steps | Output formats | Permitted destination after clearance | Quality check | Task IDs
R01 | Digital PDF or licensed article | PDF; authorized HTML capture | Preserve binary and rights; extract native text, tables, headings, page regions and figures; compare reading order; strip navigation, not source qualifications. | JSONL evidence; Markdown review view; PNG figures; cell-structured tables | Retrieval after clearance; SFT only from reviewed case records | Pages complete; units and tables match; article boundaries exact | C01 C03 C10
R02 | Scanned PDF or handwritten paper | Original PDF TIFF JPEG PNG | Render about 300 dpi; save orientation transform; OCR to region records; retain original plus derivative; verify handwriting and critical symbols manually. | PNG pages/crops; OCR JSON with boxes and quality flags | Retrieval and reviewed image/text examples | Unreadable values remain unknown; no invented characters | C04 C06 C10
R03 | Work paper or seminar slides | DOCX PPTX and linked assets | Extract paragraphs, tables, slide notes and images; retain revisions, authorship and slide anchors; export fixed-layout preview for review. | JSONL evidence; PNG figure/slide; review Markdown | Reviewed retrieval and training when specifically permitted | Notes/comments policy explicit; formulas and diagram captions retained | C05 C10
R04 | Private email or public Q and A thread | EML MBOX; MSG only via approved export | Preserve message IDs, order, timestamps and attachments; remove repeated quotes with pointers; redact personal data; label question-time evidence versus subsequent resolution. | Thread JSONL; redacted text; attachment assets | Case reconstruction only after sender/client/content rights | No later answer leaked into diagnostic prompt; attachments separately admitted | C07 D01
R05 | Diagram or equipment photograph | Original CAD/PDF and PNG/TIFF/JPEG export | Keep native original; select overview and bounded crops; annotate tags, values, arrows, regions and legibility; attach revision and equipment context. | RGB PNG/JPEG plus region/edge JSONL | Visual evidence retrieval and paired SFT examples | No hidden connectivity inferred; CAD properties not assumed from pixels | C06
R06 | Historian trend or tabular measurements | CSV XLSX Parquet approved historian export | Capture units, timezone, gauge/absolute basis, quality and missing values; retain raw observations; validate transformations; plot from checked numeric data. | Parquet numeric table; JSON dictionary; optional PNG plot | Numeric tools plus reviewed visual examples | Original numeric values preferred over digitized chart estimates | C08
R07 | Interview audio or instructional video | WAV MP3 M4A MP4 original | Record consent; transcribe with timestamps and speaker IDs; expert-correct terminology; sample meaningful frames; pair frame/time and transcript. | Transcript JSONL; selected PNGs; original recording | Text/visual curriculum; no raw audio training in release 1 | Instructor clears transcript and selected frames; no voice cloning | C09
R08 | Hugging Face instruction dataset | Pinned JSON JSONL CSV Parquet or Arrow snapshot | Review dataset and underlying source grants; inspect schema and examples; map to canonical fields; group source families; verify every domain answer; run dedup. | Approved canonical JSONL and image assets | Only admitted task-relevant records; held sources stay excluded | Dataset-card label alone is insufficient source lineage | D05 D09 D10
R09 | Foundation model or embedding model | Safetensors shards and JSON/tokenizer/processor files | Resolve full commit; preserve license/card; download pinned files; hash; load in isolated compatible environment; test image/text and adapter paths. | Pinned model directory plus manifest | Model runtime; never ingest weights as document content | Exact model, tokenizer and processor revisions work together | B02 B03 B04 B05 B06 B07
R10 | Engineering software or property data | Pinned source/package; licensed property tables | Audit license/backends; limit fluids/equations/ranges; validate independent cases; expose typed checked calculation tool. | Tool JSON schema; versioned runtime; golden fixtures | Tool execution and checked synthetic examples | Model does not invent property values or trust unvalidated simulation | E03
R11 | Catalog preview bibliography or unavailable paper | URL metadata and authorized preview | Record title, authors, edition and rights contact; seek full authoritative asset; keep catalog text out of technical case labels. | Acquisition lead only | No technical training until full asset and rights admitted | No preview presented as full book or paper | A04 A05 C02
R12 | Held benchmark or later practice source | Source metadata only at this stage | Keep excluded/NC/unknown-lineage material out; evaluate future domain fit and permissions separately; benchmarks never enter training. | Hold record or evaluator-only dataset after clearance | Deferred or evaluation only | No upstream competence inferred from refining evaluation | A04 A05 D09

## Capacity
Resource capacity and workload
Inputs are planning hours and peak weekly availability. MD/CD/technical peaks require explicit reservation; experts form a pool.
Code | Role | Planning hours | Assigned hours | Unassigned hours | Weekly peak capacity | Peak scheduled hours | Capacity review | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
MD | Managing Director | 240 | 70 | 170 | 40 | 20 | Within peak limit | 17 | 20 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1.44 | 2.4 | 6.4 | 2.4 | 2.4 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
CD | Commercial Director | 240 | 58 | 182 | 40 | 14 | Within peak limit | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 4.8 | 0 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TD | Technical Director | 480 | 184 | 296 | 40 | 20 | Within peak limit | 11.6 | 14.4 | 0 | 0 | 0 | 0 | 16.5 | 13.5 | 0 | 14.2857 | 13.7143 | 4 | 0 | 2.6667 | 5.3333 | 0 | 0 | 0 | 12 | 20 | 8 | 2 | 7 | 11.2 | 16.8 | 1.3333 | 5.3333 | 1.3333 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
PAE | Process Applications Engineer | 720 | 230 | 490 | 40 | 32.1429 | Within peak limit | 0 | 0 | 0 | 21 | 31 | 29.6 | 27.9 | 16.5 | 0 | 4.5 | 1.5 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7143 | 32.1429 | 32.1429 | 0 | 0 | 0 | 0 | 0 | 0
HP | Head of Product and AI | 480 | 136 | 344 | 40 | 21.6 | Within peak limit | 21.6 | 10.4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 13 | 0 | 14 | 0 | 0 | 0.66667 | 3.3333 | 3.3333 | 0.66667 | 0 | 0 | 7 | 8 | 12 | 3.3333 | 8.6667 | 20 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
AI | Applied AI Engineer | 960 | 447 | 513 | 40 | 32 | Within peak limit | 12 | 31.3333 | 30.6667 | 32 | 0 | 5.3333 | 10.6667 | 15 | 24 | 18 | 22 | 0 | 26 | 14 | 24 | 20 | 20.3333 | 21.6667 | 21.6667 | 4.3333 | 0 | 20.6667 | 26.8333 | 16.5 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KE | Knowledge Engineer | 960 | 465 | 495 | 40 | 37.5 | Within peak limit | 18 | 0 | 10.6667 | 32.6667 | 26.6667 | 27 | 19 | 3.3333 | 33.6667 | 17.6 | 16 | 16 | 16 | 16 | 19.9 | 22.5 | 22.5 | 22.5 | 31.5 | 37.5 | 37.3333 | 18.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SEC | Parent security lead | 160 | 119 | 41 | 40 | 20.8 | Within peak limit | 20.2 | 20.8 | 1.3333 | 2.6667 | 0 | 5 | 0 | 0 | 5 | 0 | 5.6667 | 3.3333 | 0 | 0 | 1 | 5 | 4.75 | 3.75 | 1.5 | 0 | 2 | 4 | 0 | 13.7 | 19.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXP | Contracted expert or independent reviewer | 1000 | 658 | 342 | 120 | 106.6667 | Within peak limit | 3.2 | 4.8 | 0 | 22 | 18 | 10.9 | 31.1 | 18 | 40 | 22.8571 | 17.1429 | 0 | 0 | 0 | 9 | 15 | 15 | 15 | 70 | 106.6667 | 69.3333 | 0 | 0 | 24 | 46 | 20 | 0 | 22.8571 | 28.5714 | 28.5714 | 0 | 0 | 0 | 0 | 0 | 0
OPS | Contracted implementation specialist | 300 | 213 | 87 | 40 | 33 | Within peak limit | 24 | 7 | 2 | 18 | 6 | 0 | 0 | 10 | 0 | 0 | 5.3333 | 10.6667 | 33 | 25 | 0 | 0 | 4.5 | 22.5 | 9 | 0 | 0 | 0 | 1.5 | 18.5 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hour envelopes | Earlier employee allocation: 4,080 hours.
Expert pool: 1,000 hours proposed.
Implementation specialist: 300 hours.
Parent security: 160 hours proposed.

## Weekly effort
Weekly owner and review effort
Uniform effort within each task duration. These estimates exclude unassigned overhead and buffers.
Task | Role | Work type | Total hours | Days | Start day | Finish day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
B01 | OPS | Owner | 20 | 3 | 1 | 3 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | SEC | Review | 6 | 3 | 1 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B02 | AI | Owner | 12 | 2 | 4 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B02 | OPS | Review | 4 | 2 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B03 | HP | Owner | 4 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B03 | SEC | Review | 3 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B04 | AI | Owner | 6 | 1 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B04 | OPS | Review | 3 | 1 | 6 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B05 | AI | Owner | 12 | 2 | 7 | 8 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B05 | HP | Review | 4 | 2 | 7 | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B06 | AI | Owner | 20 | 3 | 9 | 11 | 0 | 13.3333 | 6.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B06 | OPS | Review | 6 | 3 | 9 | 11 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B07 | AI | Owner | 18 | 3 | 12 | 14 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B07 | HP | Review | 4 | 3 | 12 | 14 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A01 | HP | Owner | 12 | 2 | 2 | 3 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A01 | TD | Review | 2 | 2 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A02 | MD | Owner | 10 | 3 | 1 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A02 | HP | Review | 2 | 3 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A03 | CD | Owner | 24 | 4 | 4 | 7 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A03 | HP | Review | 4 | 4 | 4 | 7 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A04 | KE | Owner | 18 | 3 | 2 | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A04 | MD | Review | 3 | 3 | 2 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A05 | MD | Owner | 20 | 5 | 5 | 9 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A05 | SEC | Review | 8 | 5 | 5 | 9 | 1.6 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A06 | SEC | Owner | 24 | 5 | 4 | 8 | 9.6 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A06 | HP | Review | 4 | 5 | 4 | 8 | 1.6 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A07 | TD | Owner | 24 | 5 | 4 | 8 | 9.6 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A07 | EXP | Review | 8 | 5 | 4 | 8 | 3.2 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G0 | MD | Owner | 4 | 1 | 10 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G0 | HP | Review | 2 | 1 | 10 | 10 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C01 | AI | Owner | 18 | 3 | 15 | 17 | 0 | 0 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C01 | SEC | Review | 4 | 3 | 15 | 17 | 0 | 0 | 1.3333 | 2.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C02 | KE | Owner | 16 | 3 | 14 | 16 | 0 | 0 | 10.6667 | 5.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C02 | MD | Review | 3 | 3 | 14 | 16 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C03 | AI | Owner | 20 | 3 | 18 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C03 | KE | Review | 6 | 3 | 18 | 20 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C04 | OPS | Owner | 24 | 4 | 18 | 21 | 0 | 0 | 0 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C04 | PAE | Review | 8 | 4 | 18 | 21 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C05 | KE | Owner | 16 | 3 | 23 | 25 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C05 | PAE | Review | 4 | 3 | 23 | 25 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C06 | PAE | Owner | 28 | 5 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 5.6 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C06 | EXP | Review | 12 | 5 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 2.4 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C07 | KE | Owner | 20 | 4 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C07 | SEC | Review | 5 | 4 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C08 | PAE | Owner | 24 | 4 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C08 | EXP | Review | 6 | 4 | 26 | 29 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09 | KE | Owner | 20 | 4 | 30 | 33 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C09 | EXP | Review | 10 | 4 | 30 | 33 | 0 | 0 | 0 | 0 | 0 | 2.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C10 | PAE | Owner | 22 | 4 | 35 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C10 | EXP | Review | 8 | 4 | 35 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C11 | AI | Owner | 16 | 3 | 30 | 32 | 0 | 0 | 0 | 0 | 0 | 5.3333 | 10.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C11 | KE | Review | 6 | 3 | 30 | 32 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C12 | OPS | Owner | 10 | 2 | 39 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C12 | AI | Review | 3 | 2 | 39 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D01 | KE | Owner | 32 | 6 | 17 | 22 | 0 | 0 | 0 | 21.3333 | 10.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D01 | EXP | Review | 24 | 6 | 17 | 22 | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D02 | TD | Owner | 12 | 2 | 33 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D02 | EXP | Review | 8 | 2 | 33 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D03 | KE | Owner | 40 | 5 | 42 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D03 | EXP | Review | 50 | 5 | 42 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D04 | TD | Owner | 18 | 4 | 35 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D04 | EXP | Review | 16 | 4 | 35 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E01 | AI | Owner | 18 | 3 | 39 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E01 | KE | Review | 5 | 3 | 39 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3333 | 1.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E02 | AI | Owner | 18 | 3 | 42 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E02 | SEC | Review | 5 | 3 | 42 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E03 | PAE | Owner | 40 | 8 | 18 | 25 | 0 | 0 | 0 | 15 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E03 | EXP | Review | 16 | 8 | 18 | 25 | 0 | 0 | 0 | 6 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1 | HP | Owner | 4 | 1 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1 | TD | Review | 4 | 1 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E04 | AI | Owner | 24 | 4 | 48 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E04 | PAE | Review | 6 | 4 | 48 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E05 | AI | Owner | 16 | 3 | 52 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E05 | SEC | Review | 4 | 3 | 52 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E06 | OPS | Owner | 16 | 3 | 55 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3333 | 10.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E06 | SEC | Review | 5 | 3 | 55 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6667 | 3.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F01 | TD | Owner | 24 | 7 | 48 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2857 | 13.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F01 | EXP | Review | 30 | 7 | 48 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8571 | 17.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F02 | HP | Owner | 10 | 2 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F02 | TD | Review | 4 | 2 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2 | MD | Owner | 4 | 1 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2 | HP | Review | 3 | 1 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D05 | KE | Owner | 80 | 25 | 48 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 16 | 16 | 16 | 16 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D05 | MD | Review | 12 | 25 | 48 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 2.4 | 2.4 | 2.4 | 2.4 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D06 | KE | Owner | 90 | 20 | 73 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5 | 22.5 | 22.5 | 22.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D06 | EXP | Review | 60 | 20 | 73 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 15 | 15 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D07 | KE | Owner | 90 | 12 | 93 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 37.5 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D07 | EXP | Review | 160 | 12 | 93 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 66.6667 | 53.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D08 | TD | Owner | 40 | 10 | 93 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D08 | EXP | Review | 80 | 10 | 93 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09 | KE | Owner | 22 | 3 | 105 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3333 | 14.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D09 | SEC | Review | 6 | 3 | 105 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D10 | AI | Owner | 14 | 2 | 108 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D10 | KE | Review | 4 | 2 | 108 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F03 | AI | Owner | 26 | 5 | 61 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F03 | OPS | Review | 8 | 5 | 61 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F04 | HP | Owner | 14 | 3 | 66 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F04 | AI | Review | 4 | 3 | 66 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F05 | AI | Owner | 30 | 6 | 69 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F05 | TD | Review | 8 | 6 | 69 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6667 | 5.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F06 | AI | Owner | 52 | 12 | 85 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3333 | 21.6667 | 21.6667 | 4.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F06 | HP | Review | 8 | 12 | 85 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 3.3333 | 3.3333 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F07 | AI | Owner | 20 | 3 | 110 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6667 | 13.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F07 | TD | Review | 6 | 3 | 110 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F08 | AI | Owner | 8 | 1 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F08 | HP | Review | 3 | 1 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3 | HP | Owner | 4 | 1 | 114 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3 | TD | Review | 3 | 1 | 114 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H01 | OPS | Owner | 50 | 10 | 61 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H01 | PAE | Review | 8 | 10 | 61 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H02 | AI | Owner | 40 | 10 | 75 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H02 | SEC | Review | 10 | 10 | 75 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H03 | AI | Owner | 22 | 4 | 115 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H03 | OPS | Review | 6 | 4 | 115 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H04 | OPS | Owner | 36 | 8 | 85 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 22.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H04 | SEC | Review | 6 | 8 | 85 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 3.75 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I01 | TD | Owner | 28 | 5 | 119 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2 | 16.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I01 | EXP | Review | 60 | 5 | 119 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I02 | SEC | Owner | 28 | 5 | 119 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2 | 16.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I02 | OPS | Review | 10 | 5 | 119 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I03 | HP | Owner | 20 | 5 | 119 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I03 | CD | Review | 8 | 5 | 119 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I04 | AI | Owner | 30 | 6 | 124 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I04 | EXP | Review | 30 | 6 | 124 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I05 | OPS | Owner | 20 | 4 | 119 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I05 | SEC | Review | 5 | 4 | 119 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I06 | HP | Owner | 10 | 3 | 130 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3333 | 6.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I06 | TD | Review | 4 | 3 | 130 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 2.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4 | MD | Owner | 4 | 1 | 133 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4 | HP | Review | 2 | 1 | 133 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J01 | CD | Owner | 18 | 3 | 134 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J01 | TD | Review | 4 | 3 | 134 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6667 | 1.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J02 | PAE | Owner | 90 | 14 | 137 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7143 | 32.1429 | 32.1429 | 0 | 0 | 0 | 0 | 0 | 0
J02 | EXP | Review | 80 | 14 | 137 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8571 | 28.5714 | 28.5714 | 0 | 0 | 0 | 0 | 0 | 0
J03 | HP | Owner | 20 | 4 | 137 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J03 | CD | Review | 8 | 4 | 137 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J04 | MD | Owner | 6 | 1 | 151 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
J04 | TD | Review | 3 | 1 | 151 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
G5 | MD | Owner | 4 | 1 | 152 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
G5 | HP | Review | 2 | 1 | 152 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0

## References
Technical references
AWS and foundation references checked 24 September 2026. Exact versions are pinned and proven during implementation.
ID | Reference | URL or record | Use
HF01 | Qwen3.5 candidate model | https://huggingface.co/Qwen/Qwen3.5-4B | Model artifacts and publisher runtime guidance
HF02 | Qwen3.5 Transformers implementation | https://huggingface.co/docs/transformers/main/en/model_doc/qwen3_5 | Model class and processor compatibility
HF03 | Hub downloads | https://huggingface.co/docs/huggingface_hub/guides/download | Pinned snapshot acquisition
HF04 | TRL dataset formats | https://huggingface.co/docs/trl/en/dataset_formats | Prompt/completion and image inputs
HF05 | TRL SFT trainer | https://huggingface.co/docs/trl/en/sft_trainer | Trainer and loss/truncation behavior
HF06 | PEFT LoRA | https://huggingface.co/docs/peft/main/package_reference/lora | Adapter configuration
HF07 | PEFT checkpoint format | https://huggingface.co/docs/peft/main/en/developer_guides/checkpoint | Adapter artifacts and base dependency
HF08 | Datasets image loading | https://huggingface.co/docs/datasets/image_load | Image dataset loading
HF09 | Embedding model | https://huggingface.co/Qwen/Qwen3-Embedding-0.6B | Candidate embedding model
HF10 | Reranker model | https://huggingface.co/Qwen/Qwen3-Reranker-0.6B | Candidate reranker
DOC01 | Docling supported formats | https://docling-project.github.io/docling/usage/supported_formats/ | Candidate extraction tool; prove on engineering samples
LOCAL01 | Existing source registers | Broadbridge_Training_Source_Register.csv and Norm_Lieberman_Source_Register.csv | Source status inherited from23 September2026 review; not new permission evidence
AWS01 | EC2 G6e instance specifications | https://aws.amazon.com/ec2/instance-types/g6e/ | Initial 48 GB GPU candidate; validate training memory on actual batches
AWS02 | AWS Deep Learning AMI releases | https://docs.aws.amazon.com/dlami/latest/devguide/appendix-ami-release-notes.html | Choose regional PyTorch GPU AMI and record exact image ID
AWS03 | Session Manager prerequisites | https://docs.aws.amazon.com/systems-manager/latest/userguide/session-manager-prerequisites.html | Agent, instance role and outbound connectivity
AWS04 | S3 sync command | https://docs.aws.amazon.com/cli/latest/reference/s3/sync.html | Copy snapshots, datasets and run artifacts